## Sheet1
Designing a Throwing Machine
My Team Name | [5 empty] | Today's Date: | 2009-02-24
(vertical red line)
| Project Lead: | ES110 Class
| Start Date: | 2012-09-01 |  | Saturday
[42] | [8 empty] | First Day of Week (Mon=2):
WBS | Tasks | Task Lead | Start | End | Duration (Days) | % Complete | Working Days | Days Complete | Days Remaining
1 | Form a group | Farid | 2012-09-01 | 2012-09-17 | 17 | 100% | 11 | 17 | 0
1.1 | get to know group members | Steve | 2012-09-01 | 2012-09-17 | 17 | 100% | 11 | 17 | 0
1.2 | domain name |  | 2012-09-18 | 2012-09-17 | 0 | 0% | -2 | 0 | 0
1.2.1 | what information? |  | 2012-09-18 | 2012-09-17 | 0 | 0% | -2 | 0 | 0
Formulas:
Start = MIN([Start, row below]:D15)
Start = [End, row above]+1
End = [Start]+[Duration (Days)]-1
Working Days = NETWORKDAYS([Start],[End])
Note on A10: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … The WBS is automatically entered, but the formulas are different for different levels.
Note on D10: Start Date Enter the starting date for this task. To associate the start date with the end of another task, enter a formula in the start date that refers to the end date of that task.
Note on E10: End Date The ending date is calculated by adding the Duration (calendar days) to the Start date minus 1 day, because the task duration is from the beginning of the Start day to the end of the End day.
Note on F10: Duration (Calendar Days) Enter the number of calendar days for the given task. Refer to the Working Days column or use a calendar to determine the corresponding working days. The duration is from the beginning of the Start date to the ending of the End Date. When the duration is calculated, it is calculated as End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day.
Note on G10: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on H10: Working Days Counts the number of working days using the NETWORKDAYS() formula, which excludes weekends. When planning work based upon the number of working days, adjust the Duration until the desired # of working days is reached.
Note on I10: Calendar Days Complete This column is calculated by multiplying the Duration by the %Complete and rounding down to the nearest integer.
Note on J10: Calendar Days Remaining This column is calculated by subtracting the Days Complete from the Duration.

## Sheet2
Designing a Throwing Machine |  | Project Lead: | ES110 Class
My Team Name |  | Start Date: | 2012-09-01
WBS | Tasks | Task Lead | Start | End | Duration (Days) | % Complete
1 | Form a group | Farid | 2012-09-01 | 2012-09-22 | 22 |  | <-- Don't Change Date
1.1 | get to know group members | Steve | 2012-09-01 | 2012-09-17 | 17 | 100%
1.2 | domain name |  | 2012-09-18 | 2012-09-17 | 0 | 23%
1.2.1 | what information? |  | 2012-09-18 | 2012-09-17 | 0 | 23%
2 | Visit Sidekicks | all | 2012-09-22 | 2012-09-22 | 0 | 24.18% | <-- Don't Change Date
2.1 | Make sure you go to sidekicks | All | 2012-09-01 | 2012-08-31 | 0 | 23%
3 | Create a blog | Farid | 2012-09-22 | 2012-10-01 | 24 |  | <-- Don't Change Date
3.1 | review previous projects | Steve | 2012-09-22 | 2012-09-26 | 5 | 100%
3.2 | Find a domain name |  | 2012-09-27 | 2012-09-28 | 2 | 23%
3.3 | Post your name and group name |  | 2012-09-29 | 2012-09-30 | 2 | 23%
4 | Post first progress report | Mary | 2012-10-01 | 2012-10-15 | 5 |  | <-- Don't Change Date
4.1 | What is the basic framework? | Steave | 2012-10-01 | 2012-10-05 | 5 | 100%
4.2 | Design Function/how does it work | Bill | 2012-10-01 | 2012-10-02 | 2 | 23%
4.3 | Release method | Steph | 2012-10-01 | 2012-10-02 | 2 | 23%
4.4 | Interface | Chris | 2012-10-01 | 2012-10-05 | 5 | 100%
4.5 | Sound | Mary | 2012-10-01 | 2012-10-02 | 2 | 23%
4.6 | Light | Mary | 2012-10-01 | 2012-10-02 | 2 | 23%
5 | First working prototype /Post | all | 2012-10-15 | 2012-10-22 | 15 |  | <-- Don't Change Date
5.1 | Must present in class | All | 2012-10-15 | 2012-10-22 | 8 | 100%
6 | Attend Last Sidekick meeting / Post | all | 2012-10-22 | 2012-10-29 | 0 |  | <-- Don't Change Date
6.1 | Must take your prototype with you | All | 2012-10-22 | 2012-10-22 | 1 | 100%
6.2 | Post a short report | All | 2012-10-22 | 2012-10-22 | 1 | 100%
7 | Post second progress report | Mary | 2012-10-29 | 2012-11-12 | 5 |  | <-- Don't Change Date
7.1 | What is the basic framework? | Steave | 2012-10-29 | 2012-11-02 | 5 | 100%
7.2 | Design Function/how does it work | Bill | 2012-10-29 | 2012-10-30 | 2 | 23%
7.3 | Release method | Steph | 2012-10-29 | 2012-10-30 | 2 | 23%
7.4 | Interface | Chris | 2012-10-29 | 2012-11-02 | 5 | 100%
7.5 | Sound | Mary | 2012-10-29 | 2012-10-30 | 2 | 23%
7.6 | Light | Mary | 2012-10-29 | 2012-10-30 | 2 | 23%
8 | Presentation/Post | all | 2012-11-12 | 2012-12-03 | 29 |  | <-- Don't Change Date
8.1 | Must present | All | 2012-11-12 | 2012-11-19 | 8 | 100%
9 | You tube presentation | all | 2012-12-03 | 2012-12-10 | 1 |  | <-- Don't Change Date
9.1 | Must be available in you blog! | All | 2012-12-03 | 2012-12-03 | 1 | 100%
Formulas:
ES110 Class = [End, row above]+1
ES110 Class = [ES110 Class, row above]
End = [ES110 Class]+[Duration (Days)]-1
Note on A3: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … The WBS is automatically entered, but the formulas are different for different levels.
Note on D3: Start Date Enter the starting date for this task. To associate the start date with the end of another task, enter a formula in the start date that refers to the end date of that task.
Note on E3: End Date The ending date is calculated by adding the Duration (calendar days) to the Start date minus 1 day, because the task duration is from the beginning of the Start day to the end of the End day.
Note on F3: Duration (Calendar Days) Enter the number of calendar days for the given task. Refer to the Working Days column or use a calendar to determine the corresponding working days. The duration is from the beginning of the Start date to the ending of the End Date. When the duration is calculated, it is calculated as End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day.
Note on G3: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).